## Gannt
PROJECT TITLE |  |  |  | PROJECT DURATION | PROJECT START DATE | PROJECT END DATE | [13 empty] | 2020 - 2021 | [9 empty] | Late
PLANA |  |  |  | 123 | 2020-09-14 | 2021-01-15
[9 empty] | September | [21 empty] | October | [30 empty] | November | [31 empty] | December | [26 empty] | Januar
[8 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Task ID | Task Name | Task Description | Priority | Task Duration (days) | Start Date | End Date planned | End Date actual | time axis 2020-09-14 to 2021-01-21
1 | Infarstructure | Set up infrastruture GitLab | High | 0.25 | 2020-09-14 | 2020-09-14 06:00 | bar: 2020-09-14
2 | User stories | Enter user stories in product backlog | High | 0.25 | 2020-09-14 | 2020-09-14 06:00 | bar: 2020-09-14
3 | Create tasks | Break down user stories to tasks for sprint1 | High | 0.25 | 2020-09-14 | 2020-09-14 06:00 | bar: 2020-09-14
4 | User story | Implement Repositories * | High | 5 | 2020-10-01 | 2020-10-06 | bar: 2020-10-02 to 2020-10-07
5 | User story | Implement PlanController | High | 5 | 2020-09-15 | 2020-09-20 | bar: 2020-09-16 to 2020-09-21
6 | Knowledges | Learn deeper about repositories methods and controllers in asp.net core | High | 2.5 | 2020-11-18 | 2020-11-20 12:00 | bar: 2020-11-19 to 2020-11-21
7 | Tests | Provide first test classes | Medium | 2.5 | 2020-12-12 | 2020-12-14 12:00 | bar: 2020-12-13 to 2020-12-15
8 | Document | Describe repostiories and controllers | Medium | 2.5 | 2021-01-05 | 2021-01-07 12:00 | bar: 2021-01-06 to 2021-01-08
9 | 0 | 0 | 0 | 0 | 2021-01-15 | 2021-01-15 | bar: 2021-01-16
10 | Milestone | Check for delivery of sprint1 | 0 | 0 | 2020-10-02 | 2020-10-02 | 2020-10-04 | bar: 2020-10-02 to 2020-10-05
0
Formulas:
PROJECT END DATE = [PROJECT START DATE]+[PROJECT DURATION]

## Project-Planning
BaThesis BTI7321 20/21, HS, Project Planning
Sprint | Calendar
Semester week | MO | FR | sprint N
1 | 2020-09-14 | 2020-09-18
2 | 2020-09-21 | 2020-09-25
3 | 2020-09-28 | 2020-10-02 | 1
4 | 2020-10-05 | 2020-10-09
5 | 2020-10-12 | 2020-10-16
6 | 2020-10-19 | 2020-10-23 | 2
7 | 2020-10-26 | 2020-10-30
8 | 2020-11-02 | 2020-11-06
9 | 2020-11-09 | 2020-11-13 | 3
10 | 2020-11-16 | 2020-11-20
11 | 2020-11-23 | 2020-11-27
12 | 2020-11-30 | 2020-12-04
13 | 2020-12-07 | 2020-12-11 | 4
14 | 2020-12-14 | 2020-12-18
Holidays | 2020-12-21 | 2020-12-25
Holidays | 2020-12-28 | 2021-01-01
15 | 2021-01-04 | 2021-01-08
16 | 2021-01-11 | 2021-01-15
| 2021-01-18 | 2021-01-22
| 2021-01-25 | 2021-01-29
| 2021-02-01 | 2021-02-05
| 2021-02-08 | 2021-02-12

## Product Backlog
Product Backlog
ID | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status
1 |  |  | Hight
2
3
4
5
6
7
8
9
10
11
12
13
14 |  |  | Medium
15
16
17

## Sprint 1
Sprint Backlog(Sprint1)
[5 empty] | 74 | 0 |  | max hours sprint1 = 100h
ID | Task Name | Task Description | duration (~ 4h per day) | Priority | Estimated Effort | Actual Effort | Status
1 | Infarstructure | Set up infrastruture GitLab | 0.25 | High | 1
2 | User stories | Enter user stories in product backlog | 0.25 | High | 1
3 | Create tasks | Break down user stories to tasks for sprint1 | 0.25 | High | 1
5 | User story | Implement Repositories * | 5 | High | 20
6 | User story | Implement PlanController | 5 | High | 20
8 | Knowledges | Learn deeper about repositories methods and controllers in asp.net core | 2.5 | High | 10
4 | Tests | Provide first test classes | 2.5 | Medium | 10
7 | Document | Describe repostiories and controllers | 2.5 | Medium | 10
9 |  |  | 0
10 | Milestone | Check for delivery of sprint1 | 0 |  | 1
11
12
13
14
15
16
17

## Sprint2
Sprint Backlog(Sprint2)
ID | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status
1 |  |  | Hight
2
3
4
5
6
7
8
9
10
11
12
13
14 |  |  | Medium
15
16
17

## Sprint 3
Sprint Backlog(Sprint3)
ID | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status
1 |  |  | Hight
2
3
4
5
6
7
8
9
10
11
12
13
14 |  |  | Medium
15
16
17

## Sprint 4
Sprint Backlog(Sprint4)
ID | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status
1 |  |  | Hight
2
3
4
5
6
7
8
9
10
11
12
13
14 |  |  | Medium
15
16
17

## excel-formula
losung= =IF(AND(G$6>=$D7,G$6<=$E7),"X",IF(AND(G$6>$E7,G$6<= $F7), "Y","")) |  |  | // this a formula if there are delate
example = =IF(AND(F$6>=$D7,F$6<=$E7),"X","") |  | // this is the basic formula for gannt
M | // this is a formula for milenstein