## Termins-rules
BaThesis BTI7321 20/21, HS, Project Planning
Appointments and Rules

## Project-Planning
BaThesis BTI7321 20/21, HS, Project Planning
Sprint | Calendar
Semester week | MO | FR | sprint N
1 | 2020-09-14 | 2020-09-18
2 | 2020-09-21 | 2020-09-25
3 | 2020-09-28 | 2020-10-02 | 1
4 | 2020-10-05 | 2020-10-09
5 | 2020-10-12 | 2020-10-16
6 | 2020-10-19 | 2020-10-23 | 2
7 | 2020-10-26 | 2020-10-30
8 | 2020-11-02 | 2020-11-06
9 | 2020-11-09 | 2020-11-13 | 3
10 | 2020-11-16 | 2020-11-20
11 | 2020-11-23 | 2020-11-27
12 | 2020-11-30 | 2020-12-04
13 | 2020-12-07 | 2020-12-11 | 4
14 | 2020-12-14 | 2020-12-18
Holidays | 2020-12-21 | 2020-12-25
Holidays | 2020-12-28 | 2021-01-01
15 | 2021-01-04 | 2021-01-08
16 | 2021-01-11 | 2021-01-15
| 2021-01-18 | 2021-01-22
| 2021-01-25 | 2021-01-29
| 2021-02-01 | 2021-02-05
| 2021-02-08 | 2021-02-12

## Gannt
BaThesis BTI7321 20/21, HS, Project Planning
PROJECT TITLE |  |  |  | PROJECT DURATION (days) | PROJECT START DATE | PROJECT END DATE | [13 empty] | 2020 - 2021 | [17 empty] | Late
PLANA |  |  |  | 124.25 | 2020-09-14 | 2021-01-16 06:00
[9 empty] | September | [21 empty] | October | [30 empty] | November | [31 empty] | December | [26 empty] | Januar
[8 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Task ID | Task Name | Task Description | Priority | Task Duration (days) | Start Date | till Date planned | End Date actual | time axis 2020-09-14 to 2021-01-31
1 | Infrastructure | Set up infrastructure GitLab | High | 0.5 | 2020-09-14 | 2020-09-14 12:00 | bar: 2020-09-14
2 | User stories | Enter user stories in product backlog | High | 0.5 | 2020-09-14 | 2020-09-14 12:00 | bar: 2020-09-14
3 | Create tasks | Break down user stories to tasks for sprint1 | High | 0.5 | 2020-09-14 | 2020-09-14 12:00 | 2020-09-14 | bar: 2020-09-14
4 | User story | Implement Repositories * | High | 5 | 2020-10-01 | 2020-10-06 | 2020-10-07 | bar: 2020-10-01 to 2020-10-07
5 | User story | Implement PlanController | High | 5 | 2020-09-15 | 2020-09-20 | bar: 2020-09-15 to 2020-09-19
6 | Knowledges | Learn deeper about repositories methods and controllers in asp.net core | High | 2.5 | 2020-11-18 | 2020-11-20 12:00 | bar: 2020-11-18 to 2020-11-20
7 | Tests | Provide first test classes | Medium | 2.5 | 2020-12-12 | 2020-12-14 12:00 | bar: 2020-12-12 to 2020-12-14
8 | Document | Describe repositories and controllers | Medium | 2.5 | 2021-01-05 | 2021-01-07 12:00 | bar: 2021-01-05 to 2021-01-07
9 | User stories | Start first steps of study director's view design with Blazor | Medium | 1.25 | 2021-01-15 | 2021-01-16 06:00 | bar: 2021-01-15 to 2021-01-16
10 | Milestone | delivery of sprint1 | Milestone | 0 | 2020-10-02 | 2020-10-02 | bar: 2020-10-02
Formulas:
PROJECT END DATE = [PROJECT START DATE]+[PROJECT DURATION (days)]

## Product Backlog
BaThesis BTI7321 20/21, HS, Project Planning
Product Backlog
ID | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status
1 | Make a plan of assignments | As a study director, I want to be able to make a concrete plan of assignments for lecturers for the coming year as well as a provision plan for the next 2-3 years, so the teachers can be better informed about their work hours and schedule for the next several years. And it will be easier to add new small changes into the employment plan. | High
2 | Manage plan of assignments
3
4
5
6
7
8
9
10
11
12
13
14 |  |  | Medium
15
16
17

## Sprint 1
BaThesis BTI7321 20/21, HS, Project Planning
Sprint Backlog(Sprint1) |  |  |  |  | tot hours per sprint
[5 empty] | 91 | 0 |  | max hs sprint1
ID | Task Name | Task Description | duration in days | Priority | Estimated Effort | Actual Effort | Status | 100
1 | Infrastructure | Set up infrastructure GitLab | 0.5 | High | 2
4 | Management tools | Create project management document structure(PB, sprints, gannt diagramm ) | 2.5 | High | 10
2 | User stories | Enter user stories in product backlog | 0.5 | High | 2
3 | Create tasks | Break down user stories to tasks for sprint1 | 0.5 | High | 2
5 |  |  | 5 | High | 20
6 |  |  | 5 | High | 20
8 |  |  | 2.5 | High | 10
4 |  |  | 2.5 | Medium | 10
7 |  |  | 2.5 | Medium | 10
9 | User stories | Start first steps of study director's view design with Blazor | 1.25 | Medium | 5
10 | Milestone | delivery of sprint1 | 0 | Milestone | 0
deliverable 1
Goals
Organize project management
Organize product backlog :
- PL item prioritization
Organize sprint
- fix the list of PB for this sprint
- split big PB in smaller items
- schedule the tasks using gannt diagram
-Think about the main view for planning of assignments
-Start implementation a view with blazor
-In parallel with implementation of api describe it in the main report
Component of Deliverable 1
Project Management document with structure for : -PB , - Sprint 1, gannt diagram
Enter content for PB at the beginning of the sprint
Enter priority to the tasks
Planner Controller (min -start it)
Repositories
View -> Planner ->start state

## Sprint2
BaThesis BTI7321 20/21, HS, Project Planning
Sprint Backlog(Sprint2) |  |  |  |  | tot hours per sprint
[5 empty] | 0 | 0 |  | max hs sprint1 = 100h
ID | Task Name | Task Description | duration in days | Priority | Estimated Effort | Actual Effort | Status
Seed data
| User story | Implement Repositories *
| User story | Implement PlanController
| Knowledges | Learn deeper about repositories methods and controllers in asp.net core
| Tests | Provide first test classes
| Document | Describe repositories and controllers
deliverable 2
goals
Organize product backlog :
- PL item prioritization
Organize sprint
- fix the list of PB for this sprint
- split big PB in smaller items
- schedule the tasks using gannt diagram
- Implementation of repositories
- Start with PlannerController
Component of Deliverable 2

## Sprint 3
BaThesis BTI7321 20/21, HS, Project Planning
Sprint Backlog(Sprint3) |  |  |  |  | tot hours per sprint
[5 empty] | 0 | 0 |  | max hs sprint1 = 100h
ID | Task Name | Task Description | duration in days | Priority | Estimated Effort | Actual Effort | Status
deliverable 3
Goals
Component of Deliverable 3

## Sprint 4
BaThesis BTI7321 20/21, HS, Project Planning
Sprint Backlog(Sprint4) |  |  |  |  | tot hours per sprint
[5 empty] | 0 | 0 |  | max hs sprint1 = 100h
ID | Task Name | Task Description | duration in days | Priority | Estimated Effort | Actual Effort | Status
deliverable 4

## excel-formula
losung= =IF(AND(G$6>=$D7,G$6<=$E7),"X",IF(AND(G$6>$E7,G$6<= $F7), "Y","")) |  |  | // this a formula if there are delate
example = =IF(AND(F$6>=$D7,F$6<=$E7),"X","") |  | // this is the basic formula for gannt
M | // this is a formula for milenstein
the main formula for gannt = IF(AND(I$6=$F7,$E7=0),"u", IF(AND(I$6>=$F7,I$6<$G7),"X",IF(AND(I$6>=$G7,I$6<=$H7),"Y","")))
// = TODAY() Current date (varies) // =NOW() Current date and time (varies)

## work-control
project
|  | start | end | h
seed data, repositories |  |  |  | 0:00
models, 1st test | 2020-08-18 | 15:45 | 19:30 | 3:45
| 2020-08-19 |  |  | 0:00
| 2020-08-20 |  |  | 0:00
| 2020-08-21 |  |  | 0:00
| 2020-08-22 |  |  | 0:00
| 2020-08-23 |  |  | 0:00
| 2020-08-24 |  |  | 0:00
| 2020-08-25 |  |  | 0:00
| 2020-08-26 |  |  | 0:00
| 2020-08-27 |  |  | 0:00
| 2020-08-28 |  |  | 0:00
| 2020-08-29 |  |  | 0:00
| 2020-08-30 |  |  | 0:00
| 2020-08-31 |  |  | 0:00
| 2020-09-01 |  |  | 0:00
2020-09-02
2020-09-03
2020-09-04
2020-09-05
2020-09-06
2020-09-07
2020-09-08
2020-09-09
2020-09-10
2020-09-11
2020-09-12
2020-09-13
2020-09-14
2020-09-15
2020-09-16
2020-09-17
2020-09-18