## Termins-rules
BaThesis BTI7321 20/21, HS, Project Planning |  |  |  |  | Ablauf der Bachelor-Thesis / Milestones
Appointments and Rules
|  | date | time | Woche
|  |  |  | 1 | Start Bachelor-Thesis Montag 08h00
|  |  |  | 1 -- 2 | Festlegen des Deliverables und deren Termine
|  |  |  | 1 -- 16 | Regelmässige Treffen
| 2021-01-21 | 2021-01-21 | 20h00 | 16 | Abgabe Projektdokumentation an Betreuer/in und Experten/Expertin; zusätzlich ein Exemplar ans Sekretariat (Archivierung). Eine elektronische Version muss z.Hd. der Abteilung abgegeben werden; Informationen dazu folgen
| 2021-01-22 | 2021-01-22 | vormittag | Finaltag | Kurzpräsentation im Rahmen des Finaltages
| 2021-01-22 | 2021-01-22 | 14h00-18h00 | Ausstellung | Öffentliche Ausstellung der Bachelor-Thesis mit Präsenz der Studierenden
| 2021-01-21 | 2021-01-21 | 20h00 | Ende Woche 17, | Abgabe Kurz-Film | -> Moodle
|  | 25.01.21 - 10.02.21 |  | Prüfungswochen | Verteidigung mit Betreuer/in und Experte/Expertin
|  | till 1.12.20 |  |  | Betreuer vereinbaren Ort und Zeit der Prüfung (zwischen 25.1. und
10.2.21) mit Experten und Studierenden und melden den Termin an
ARB1
|  | ca Oct/Nov |  |  | Abgabe Texte/Graphiken/etc. für das “Book” | wird direkt durch das Sekretariat
(Silvia.Gasenzer@bfh.ch)
[5 empty] | Abgabe elektronische Version des Posters | gem. Moodle (Heinz.Kipfer@bfh.ch)
|  | till 7Jan2021 |  | book | book ---> Mr.Pfahrer

## Project-Planning
BaThesis BTI7321 20/21, HS, Project Planning
Sprint | Calendar |  |  |  | Ablauf der Bachelor-Thesis / Milestones
Semester week | MO | FR | sprint N | merge-date |  | calendar
1 | 2020-09-14 | 2020-09-18
2 | 2020-09-21 | 2020-09-25
3 | 2020-09-28 | 2020-10-02 | 1
4 | 2020-10-05 | 2020-10-09 |  | 2020-10-11
5 | 2020-10-12 | 2020-10-16
6 | 2020-10-19 | 2020-10-23 | 2
7 | 2020-10-26 | 2020-10-30
8 | 2020-11-02 | 2020-11-06 |  | 2020-11-08
9 | 2020-11-09 | 2020-11-13 | 3
10 | 2020-11-16 | 2020-11-20
11 | 2020-11-23 | 2020-11-27
12 | 2020-11-30 | 2020-12-04
13 | 2020-12-07 | 2020-12-11 |  | 2020-12-13
14 | 2020-12-14 | 2020-12-18 | 4
Holidays | 2020-12-21 | 2020-12-25
Holidays | 2020-12-28 | 2021-01-01
Holidays15 | 2021-01-04 | 2021-01-08 |  | 2020-01-10
16 | 2021-01-11 | 2021-01-15 | 5
| 2021-01-18 | 2021-01-22 |  | 2020-01-21
| 2021-01-25 | 2021-01-29
| 2021-02-01 | 2021-02-05
| 2021-02-08 | 2021-02-12
Until this date I have to prepare all documents and also the application
All documents are:
1. Report
2. Final presentation
3. Small presentation
4. Poster
5. Video
* have to be prepared for the 1st Presentation -"Sale Product" Presentation
7-Jan
book --> Mr.Pfahrer

## Gannt
BaThesis BTI7321 20/21, HS, Project Planning
PROJECT TITLE |  |  |  | PROJECT DURATION (days) |  | PROJECT START DATE | PROJECT END DATE | [13 empty] | 2020 - 2021 | [17 empty] | Late
PLANA |  |  |  | 16.7222 |  | 2020-09-14 | 2020-09-30 17:20
sprint 1
[10 empty] | September | [21 empty] | October | [30 empty] | November | [31 empty] | December | [26 empty] | Januar
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Task ID | Task Name | Task Description | Priority | Task Duration (days) |  | Start | End planned | End actual | time axis 2020-09-14 to 2021-01-31
sprint1
1 | Infrastructure |  | High | 0.38889 | 0.38889 | 2020-09-14 | 2020-09-14 09:20 | bar: 2020-09-14
2 | Management tools |  | High | 1.9444 | 2.3333 | 2020-09-14 09:20 | 2020-09-16 08:00 | bar: 2020-09-15 to 2020-09-16
3 | Create a user stories |  | High | 0.97222 | 3.3056 | 2020-09-16 08:00 | 2020-09-17 07:20 | bar: 2020-09-17
4 | Create the tasks |  | High | 0.38889 | 3.6944 | 2020-09-17 07:20 | 2020-09-17 16:40
5 | User stories |  | High | 3.8889 | 7.5833 | 2020-09-17 16:40 | 2020-09-21 14:00 | bar: 2020-09-18 to 2020-09-21
6 | User stories |  | High | 3.8889 | 11.4722 | 2020-09-21 14:00 | 2020-09-25 11:20 | bar: 2020-09-22 to 2020-09-25
7 | User story |  | High | 1.9444 | 13.4167 | 2020-09-25 11:20 | 2020-09-27 10:00 | bar: 2020-09-26 to 2020-09-27
8 | Report |  | Medium | 1.3611 | 14.7778 | 2020-09-27 10:00 | 2020-09-28 18:40 | bar: 2020-09-28
9 | Report |  | Medium | 0.58333 | 15.3611 | 2020-09-28 18:40 | 2020-09-29 08:40 | bar: 2020-09-29
10 | Add Semester View |  | Medium | 1.3611 | 16.7222 | 2020-09-29 08:40 | 2020-09-30 17:20 | bar: 2020-09-30
11 | Frontend-Backend |  | Medium | 1.9444 | 18.6667 | 2020-09-30 17:20 | 2020-10-02 16:00 | bar: 2020-10-01 to 2020-10-02
12 | Report |  | Medium | 0.29167 | 18.9583 | 2020-10-02 16:00 | 2020-10-02 23:00
13 | Milestone |  | Milestone | 0 | 18.9583 | 2020-10-02 23:00 | 2020-10-02 23:00
Formulas:
PROJECT START DATE = [PROJECT END DATE]+(-[PROJECT DURATION (days)])

## Product Backlog
BaThesis BTI7321 20/21, HS, Project Planning
Product Backlog |  | Provision, actual is in report
ID | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | notes
1 | Create a plan of assignments | As a study director, I want to be able to make a plan of assignments for lecturers . | High |  |  | doing
2 | Manage plan of assignments | As a study director, I want to be able to manage a plan of assignments for lecturers . | High
3 | Make own plan. | As a lecturer,I want to be able to add Module Runs in my provision plan. | High |  |  |  | Ask Mr.Pfahrer if it's like this | yes
4 | Manage my plan. | As a lecturer, I want to be able to manage the plan of my assignments. | High
6 | Make a group of lecturers. | As a study director, I want to be able to add groups of lecturers to the module run. | High
5 | Make a group of modules. | As a study director, I want to be able to make a group of module runs. | High |  |  |  | Ask Mr.Pfahrer if it's like this | yes
7 | Create a lecturer subgroup . | As a lecturer, I want to be able to create a subgroup with another lecturer/s. | High |  |  |  | Ask Mr.Pfahrer if it's like this | yes but just not the main user story
8 |  |  | low
9
10
11
12
13
14 |  |  | Medium
15
16
17

## Sprint 1
BaThesis BTI7321 20/21, HS, Project Planning | [8 empty] | hours per day
Sprint Backlog(Sprint1) |  |  |  |  | hours per day | tot hours per sprint | actual |  | 4
4 | weeks |  |  |  | 5.1429 | 97.5 | 108.5 |  | hs sprint1
ID | Task Name | Task Description | days-duration | sum of days | Priority | Estimated Effort | Actual Effort | Status | 102.8571
1 | Infrastructure | Set up infrastructure GitLab | 0.38889 | 0.38889 | High | 2 | 2 | done
2 | Management tools | Create project management document structure( sprints, gannt diagramm ) | 1.9444 | 2.3333 | High | 10 | 11 | done
3 | Create a user stories | Create and enter a user stories in product backlog | 0.97222 | 3.3056 | High | 5 | 6 | done
4 | Create the tasks | Break down user stories to the tasks for sprint1 | 0.38889 | 3.6944 | High | 2 | 3 | done
5 | User stories | Make repositories | 3.8889 | 7.5833 | High | 20 | 22 | done
6 | User stories | Add controllers for crud operations | 3.8889 | 11.4722 | High | 20 | 25 | done
7 | User story | Make graphical concepts(start) | 1.9444 | 13.4167 | High | 10 | 10 | done
8 | Report | Add intoduction | 1.3611 | 14.7778 | Medium | 7 | 7 | done
9 | Report | Add background to the introduction | 0.58333 | 15.3611 | Medium | 3 | 1 | doing
10 | Add Semester View | Start with views | 1.3611 | 16.7222 | Medium | 7 | 8 | doing
11 | Frontend-Backend | Add classes to communicate view with controller | 1.9444 | 18.6667 | Medium | 10 | 12 | done
12 | Report | Add a document structure | 0.29167 | 18.9583 | Medium | 1.5 | 1.5 | done
13 | Milestone | delivery of sprint1 | 0 | 18.9583 | Milestone | 0
14
15 | Report | Add background to the introduction section of the report
deliverable sprint 1:
Goals
Organize project management
Organize Product Backlog(PB) :
- PB item prioritization
Organize sprint
- fix the list of PB for this sprint
- split big PB in smaller items
- schedule the tasks using gannt diagram
Components of Deliverable 1:
Project Management document with structure for : - Sprint 1, gannt diagram
Enter content for the PB at the beginning of the sprint
Enter priority to the tasks
concepts:
UI concepts
code:
Repositories
Controllers
report: ->
Structure
Intorduction
Product Backlog
Description of code in parallel with a code state.
The main aspects of Sprint 1 were:
1. Creation of project management.
2.Define the user stories
3. Creating of ducument structure.
4. Creating concept of User Interface

## Sprint2
BaThesis BTI7321 20/21, HS, Project Planning | [8 empty] | hours per day
Sprint Backlog(Sprint2) |  |  |  |  | hours per day | tot hours per sprint | actual
4 | weeks |  |  |  | 5.1429 | 89 | 79 |  | hs sprint1
ID | Task Name | Task Description | days-duration | sum of days | Priority | Estimated Effort | Actual Effort | Status | 102.8571
16 | Product Backlog | Add user stories |  |  | High | 1 | 1.5 | done
15 | Create the tasks | Break down user stories for the sprint2 | 0.29167 | 0.29167 | High | 1.5 | 1.5 | done
17 | UI concepts | Continue with UI concepts | 2.3333 | 2.625 | High | 12 | 15 | done
18 | Domain model | Add new concepts to the domain model | 1.1667 | 3.7917 | High | 6 | 6 | done
19 | Frontend | Display module run for one concrete semester(start) | 2.9167 | 6.7083 | High | 15 | 17 | doing
20 | UML | UML class diagram(start) | 1.3611 | 8.0694 | Medium | 7 | >>sprint3 | todo
21 | backend | Build new entities in backend, connect it to the whole programm | 1.9444 | 10.0139 | High | 10 | 11 | done
22 | User stories | Add repositories | 2.9167 |  |  | 15 | 15 | done
23 | test | Testing with postman | 0.29167 | 10.3056 | High | 1.5 | 2 | done
24 | frontend | Iclude groups into the views | 1.9444 | 12.25 |  | 10 | >> sprint3 | todo
25 | report | Describe domain model | 0.58333 | 12.8333 |  | 3 | 3 | done
26 | report | Describe innovation in the report inroduction | 0.38889 | 13.2222 |  | 2 | 2.5 | done
27 | concepts | Improve UI look | 1.1667 | 14.3889 |  | 6 | 6 | done
|  |  | 0 | 14.3889
| Milestone | delivery of sprint2 | 0 |  | Milestone | 0
deliverable sprint 2:
Goals
Organize Product Backlog(PB) :
- PB item prioritization
Organize sprint
- fix the list of PB for this sprint
- split big PB in smaller items
- schedule the tasks using gannt diagram
Components of Deliverable 2:
Enter content for the PB at the beginning of the sprint
Enter priority to the tasks
concepts:
UI concepts end look
code:
new enities
new repositories
new cotrollers
Frontend
Views include the groups
report: ->
Domain model
Inroduction extendet
Description of code in parallel with a code state.
The main aspects of Sprint 2 were:
1. Domain model
2. Final view of UI concepts
3. Add new entities in code
4.Add repositories in code
5. Extensiton of introduction

## Sprint 3
BaThesis BTI7321 20/21, HS, Project Planning | [8 empty] | hours per day
Sprint Backlog(Sprint3) |  |  |  |  | hours per day | tot hours per sprint | actual
5 | weeks |  |  |  | 5.1429 | 110.5 | 125.5 |  | hs sprint1
ID | Task Name | Task Description | days-duration | sum of days | Priority | Estimated Effort | Actual Effort | Status | 128.5714
28 | Product Backlog | Add user stories |  |  | High | 1 | 1 | done
35 | Create the tasks | Break down user stories for the sprint3 | 0.29167 | 0.29167 | High | 1.5 | 1.5 | done
36 | UI concepts | Describe UI concepts in the report | 1.5556 | 1.8472 | High | 8 | 9 | doing
56 | Backend | Add Controllers | 2.3333 | 4.1806 | High | 12 | 12 | doing
38 | Testing | Test Controllers with postman | 0.97222 | 5.1528 | High | 5 | 8 | done
20 | UML | UML class diagram | 1.3611 | 6.5139 | High | 7 | 0 | >>>
33 | Frontend | Add new views according UI concepts | 2.9167 | 9.4306 | High | 15 | 25 | done
40 | Backend-Frontend | Connect Backend and Frontend for new views | 3.8889 |  | High | 20 | 22 | doing
41 | Testing | Test functionality of the new views | 1.3611 | 10.7917 | High | 7 | 8 | doing
42 | Report | Add layer diagram | 1.5556 | 12.3472 | Medium | 8 | 8 | done
37 | Backend | Adding functionality for new classes | 2.3333 | 14.6806 | Medium | 12 | 15 | doing
44 | Architecture | Make architecture clear. | 2.9167 | 17.5972 | High | 15 | 17 | doing
39 | Frontend | Add modules view for study director | 0 | 17.5972
43 | Backend | Functionality for new classes | 0 | 17.5972
| Milestone | delivery of sprint3 | 0 |  | Milestone | 0
deliverable sprint 3:
Goals
Organize Product Backlog(PB) :
- PB item prioritization
Organize sprint
- fix the list of PB for this sprint
- split big PB in smaller items
- schedule the tasks using gannt diagram
Components of Deliverable 3:
Enter content for the PB at the beginning of the sprint
Enter priority to the tasks
concepts: UI concepts description in report
code: Controllers , new Views, Connection Backend-Frontend
report: -> UML classen diagram, Layer diagram
brake plan into days plan
report
describe layers and architecture , add layer diagram, finish sith ui requirements and UI in general
code
23-Nov > finish with all repo and make services
24,25,26,27-Nov add backend logic into services
28,29-Nov write new controllers
28,29 - implement UIs

## Sprint 4
BaThesis BTI7321 20/21, HS, Project Planning | [8 empty] | hours per day
Sprint Backlog(Sprint4) |  |  |  |  | hours per day | tot hours per sprint | actual
4 | weeks |  |  |  | 5.1429 | 129.5 | 0 |  | hs sprint1
ID | Task Name | Task Description | days-duration | sum of days | Priority | Estimated Effort | Actual Effort | Status | 102.8571
55 | Product Backlog | Add user stories |  |  | High | 1
54 | Create the tasks | Break down user stories for the sprint4 | 0.29167 | 0.29167 | High | 1.5
45 | Frontend | add all lecturer and study director views | 7.7778 | 8.0694 | High | 40
46 | Frontend-Backend | Connect backend with new frontend | 5.8333 | 13.9028 | High | 30
47 | Frontend | Add authorization to the frontend | 2.9167 | 16.8194 | High | 15
48 | Frontend | Add login page | 2.5278 | 19.3472 | Medium | 13
49 | Backend | Add methods for the work hours calculation | 1.5556 | 20.9028 | High | 8
| User stories |  | 0
50 | Book | Create book page | 0.97222 | 21.875 | High | 5
51 | Report | Add test section to the report | 0.97222 | 22.8472 | High | 5
52 | Report | Expand the project management section in the report | 0.97222 | 23.8194 | High | 5
53 | Report | UML class diagram | 1.3611 | 25.1806 | High | 7
| Reprort |  | 0 | 25.1806
|  |  | 0 | 25.1806
| Milestone | delivery of sprint2 | 0 | 25.1806 | Milestone | 0
deliverable 4
Goals:
Organize Product Backlog(PB) :
- PB item prioritization
Organize sprint
- fix the list of PB for this sprint
- split big PB in smaller items
Components of Deliverable 4:
Enter content for the PB at the beginning of the sprint
Enter priority to the tasks
code: Controllers , all Views, Connection Backend-Frontend, main functionality of the apllication has to have status: "done"
report: -> UML class diagram, test section, management section

## excel-formula
losung= =IF(AND(G$6>=$D7,G$6<=$E7),"X",IF(AND(G$6>$E7,G$6<= $F7), "Y","")) |  |  | // this a formula if there are delate
example = =IF(AND(F$6>=$D7,F$6<=$E7),"X","") |  | // this is the basic formula for gannt
M | // this is a formula for milenstein
the main formula for gannt = IF(AND(I$6=$F7,$E7=0),"u", IF(AND(I$6>=$F7,I$6<$G7),"X",IF(AND(I$6>=$G7,I$6<=$H7),"Y","")))
// = TODAY() Current date (varies) // =NOW() Current date and time (varies)
360/14/5 | total hours/ 14 sprint weeks / 5 working days